## Sheet1
Phase | Activity | Responsibility | Wk1 | Wk2 | Wk3 | Wk4
Discovery Phase | Kick-off | Payobook / Thaco
| Receive all Salary schema excel sheets with working formulas eg Logistics , Retail, Office etc | Thaco
| Receive templates for Govt reports to be generated | Thaco
| Receive templates for Bank export files to be generated | Thaco
| Clarification complete on Mid-Cycle to End-cycle components | Payobook / Thaco
| Finalize understanding of Schemas | Payobook / Thaco
| Finalize Roles and access to various functionalities | Payobook / Thaco
| Finalize reports and charts | Payobook / Thaco
| Acceptance Criteria Sign-off | Thaco
Infra Setup phase | Setup of Ubuntu servers - Dev , Test , Pre-prod ?? , Production | Payobook / Thaco
| Setup of email | Thaco
| Security certificates, Firewalls , Whitelisting etc | Thaco
| Deploy applicatin in all servers | Paybook
Configuration Phase | Configuration of Salary Structure | Payobook
| Configuration of Roles | Payobook
| Configuration of Bank Export | Payobook
| Configuration of Government Reports | Payobook
| Competion of any customisation required | Payobook
| Unit Testing and Validation | Payobook
SIT & User Testing | Demo to UAT users | Payobook / Thaco
| User acceptance testing | Thaco
| UAT Sign-off | Thaco
Go-live | Deployment to Production - working and UAT tested application | Payobook
| Validation of latest payslip data - coparision with Payobook | Payobook
| Run Payslip in Payobook + Excel in parallel to validate | Thaco
Hypercare | Hypercare Support from Payobook | Payobook |  |  |  |  | 4 weeks