## Timeline - Gantt Chart
Phase | Activity | Responsibility | Wk1 | Wk2 | Wk3 | Wk4
Discovery Phase | Kick-off | Payobook / Thaco
| Receive all Salary schema excel sheets with working formulas eg Logistics , Retail, Office etc | Thaco
| Receive templates for Govt reports to be generated | Thaco
| Receive templates for Bank export files to be generated | Thaco
| Clarification complete on Mid-Cycle to End-cycle components | Payobook / Thaco
| Finalize understanding of Schemas | Payobook / Thaco
| Finalize Roles and access to various functionalities | Payobook / Thaco
| Finalize reports and charts | Payobook / Thaco
| Acceptance Criteria Sign-off | Thaco
Infra Setup phase | Setup of Ubuntu servers - Dev , Test , Pre-prod ?? , Production | Payobook / Thaco
| Setup of email | Thaco
| Security certificates, Firewalls , Whitelisting etc | Thaco
| Deploy applicatin in all servers | Paybook
Configuration Phase | Configuration of Salary Structure | Payobook
| Configuration of Roles | Payobook
| Configuration of Bank Export | Payobook
| Configuration of Government Reports | Payobook
| Competion of any customisation required | Payobook
| Unit Testing and Validation | Payobook
SIT & User Testing | Demo to UAT users | Payobook / Thaco
| User acceptance testing | Thaco
| UAT Sign-off | Thaco
Go-live | Deployment to Production - working and UAT tested application | Payobook
| Validation of latest payslip data - coparision with Payobook | Payobook
| Run Payslip in Payobook + Excel in parallel to validate | Thaco
Hypercare | Hypercare Support from Payobook | Payobook |  |  |  |  | 4 weeks

## Implementation -Phase 1-4,5-6
Giai đoạn /Phase | Hoạt động/Activity | Trách nhiệm Khách hàng/Client Responsibility | Trách nhiệm Nhà cung cấp/Vendor Responsibility | Sản phẩm bàn giao/ | Phụ thuộc từ Khách hàng/Client Dependencies
Deliverables
1 | Tổ chức họp khởi động dự án và thiết lập cơ cấu quản trị/Conduct project kick-off meeting and establish project governance | Thực hiện/Responsible | Chịu trách nhiệm chính/Accountable | Điều lệ dự án, Mô hình quản trị/Project Charter, Governance Model | Chỉ định nhà tài trợ và người ra quyết định/Nomination of sponsor and decision-makers
1 | Thu thập file Excel cấu trúc lương và công thức tính/Obtain salary structure Excel files including formulas | Chịu trách nhiệm chính/Accountable | Thực hiện/Responsible | Tài liệu cấu trúc lương được phê duyệt/Approved salary structure documentation | Mô hình bảng lương đầy đủ và chính xác/Complete and accurate payroll models
1 | Thu thập mẫu báo cáo theo quy định pháp luật/nhà nước/Obtain statutory/government report templates | Chịu trách nhiệm chính/Accountable | Thực hiện/Responsible | Mẫu báo cáo được phê duyệt/Approved report templates | Định dạng báo cáo theo quy định/Statutory formats
1 | Thu thập đặc tả file chuyển khoản/xuất dữ liệu ngân hàng/Obtain bank transfer/export specifications | Chịu trách nhiệm chính/Accountable | Thực hiện/Responsible | Đặc tả file ngân hàng được phê duyệt/Approved bank file specifications | Định dạng file ngân hàng/Bank file formats
1 | Làm rõ các thành phần lương giữa kỳ và cuối kỳ/Clarify mid-cycle and end-cycle payroll components | Thực hiện/Responsible | Thực hiện/Responsible | Tài liệu quy trình tính lương/Payroll process documentation | Làm rõ quy trình nghiệp vụ/Business process clarification
1 | Hoàn thiện cấu trúc lương và phương pháp tính/Finalize salary structures and calculation methods | Thực hiện/Responsible | Thực hiện/Responsible | Tài liệu thiết kế cấu trúc lương/Salary structure design document | Xác nhận nghiệp vụ/Business validation
1 | Hoàn thiện vai trò người dùng và ma trận phân quyền/Finalize user roles and access matrix | Chịu trách nhiệm chính/Accountable | Thực hiện/Responsible | Ma trận phân quyền truy cập/Access control matrix | Định nghĩa vai trò người dùng/Role definitions
1 | Hoàn thiện yêu cầu báo cáo và bảng điều khiển/Finalize reporting and dashboard requirements | Thực hiện/Responsible | Thực hiện/Responsible | Tài liệu đặc tả báo cáo/Reporting specification document | Xác nhận từ phía nghiệp vụ/Business confirmation
1 | Phê duyệt chính thức phạm vi và tiêu chí nghiệm thu/Formal sign-off on scope and acceptance criteria | Chịu trách nhiệm chính/Accountable | Thực hiện/Responsible | Văn bản phê duyệt phạm vi & nghiệm thu/Signed Scope and Acceptance Criteria | Phê duyệt chính thức/Formal approval
2 | Cung cấp và cấu hình máy chủ cho Test, QA và Production/Provision and configure servers for Test, QA and Production | Thực hiện/Responsible | Tham vấn/Consulted | Môi trường máy chủ đã được cấu hình/Configured server environments | Sẵn sàng hạ tầng/Infrastructure readiness
2 | Cấu hình dịch vụ email/Configure email services | Thực hiện/Responsible | Tham vấn/Consulted | Thiết lập tích hợp email/Email integration setup | Thông tin SMTP/SMTP details
2 | Triển khai các biện pháp bảo mật (SSL, tường lửa, IP)/Implement security controls (SSL, firewall, IP) | Thực hiện/Responsible | Tham vấn/Consulted | Báo cáo cấu hình bảo mật/Security configuration report | Phê duyệt an ninh & mạng/Security approvals
2 | Triển khai ứng dụng trên các môi trường/Deploy application across environments | Tham vấn/Consulted | Thực hiện/Responsible | Xác nhận triển khai hệ thống/Deployment confirmation | Máy chủ sẵn sàng/Server readiness
3 | Cấu hình cấu trúc lương/Configure salary structures | Tham vấn/Consulted | Thực hiện/Responsible | Quy tắc tính lương đã cấu hình/Configured payroll rules | Yêu cầu đã được phê duyệt/Approved requirements
3 | Cấu hình vai trò và phân quyền người dùng/Configure user roles and permissions | Tham vấn/Consulted | Thực hiện/Responsible | Xác nhận phân quyền truy cập/Access setup confirmation | Phê duyệt vai trò/Role approval
3 | Cấu hình định dạng xuất dữ liệu ngân hàng/Configure bank export formats | Tham vấn/Consulted | Thực hiện/Responsible | File xuất dữ liệu ngân hàng/Bank export files | Đặc tả ngân hàng/Bank specifications
3 | Thực hiện kiểm thử đơn vị/Perform unit testing | Tham vấn/Consulted | Thực hiện/Responsible | Báo cáo kiểm thử đơn vị/Unit test report | Dữ liệu kiểm thử/Test data
4 | Chuẩn bị và thực hiện SIT/Prepare and execute SIT | Tham vấn/Consulted | Thực hiện/Responsible | Kết quả SIT và danh sách lỗi/SIT results and defect log | Dữ liệu và kịch bản đã phê duyệt/Approved data and scenarios
4 | Chuẩn bị và thực hiện UAT/Prepare and execute UAT | Thực hiện/Responsible | Tham vấn/Consulted | Báo cáo kết quả UAT/UAT results report | Kịch bản UAT đã phê duyệt/Approved UAT scenarios
4 | Phê duyệt chính thức kết quả UAT/Formal UAT sign-off | Chịu trách nhiệm chính/Accountable | Tham vấn/Consulted | Văn bản phê duyệt UAT/Signed UAT approval | Phê duyệt của Ban quản lý/Management approval
5 | Triển khai giải pháp đã được phê duyệt lên Production/Deploy UAT-approved solution to Production | Tham vấn/Consulted | Thực hiện/Responsible | Xác nhận hệ thống vận hành chính thức/Live system confirmation | Phê duyệt cuối cùng/Final approval
6 | Chạy song song bảng lương và xác nhận kết quả/Execute parallel payroll run and validation | Thực hiện/Responsible | Thực hiện/Responsible | Báo cáo đối soát và xác nhận/Reconciliation and validation reports | Bảng lương tham chiếu/Reference payroll data
6 | Hỗ trợ tăng cường sau Go-Live/Provide post go-live hypercare support | Tham vấn/Consulted | Thực hiện/Responsible | Nhật ký hỗ trợ/Support logs | Báo cáo sự cố/Issue reporting

## System Requirements
Category | Requirement | Updated Sizing / Details
Infra – Server & OS | User sizing | ~100 Concurrent / 300 HR users
| Employee data volume | ~30,000 employees
| Operating System | Ubuntu 22.04 LTS
| CPU | 8–12 vCPU (12 vCPU recommended for payroll runs & reporting peaks)
| Memory | 32–64 GB RAM (64 GB recommended for smooth month-end processing)
| Storage | 500 GB – 1 TB SSD (includes DB growth, logs, backups, documents)
Access & Remote Installation | Server access | Access to Ubuntu server(s)
| Remote connectivity | VPN access (preferred) or Bastion / Jump host with static public IP
| SSH access | Key-based authentication only
| User privileges | Linux user with sudo privileges
Network & Security | Firewall – inbound ports | SSH (22), HTTPS (443), HTTP (80 – SSL redirect/setup), Application port (8069)
| Internet access | Outbound internet access for OS, package, and security updates
| Load handling (recommended) | Reverse proxy (Nginx) for SSL termination and performance
Domain & SSL | Domain / Subdomain | Client-provided domain or subdomain
| DNS configuration | A record pointing to server public IP or load balancer
| SSL certificate | Let’s Encrypt or client-provided SSL certificate
Backups | Backup policy | Daily automated backups
| Backup scope | Database + file store + configuration
| Retention (recommended) | 7 daily, 4 weekly, 3 monthly
Scalability (Optional but Advised) | Horizontal scaling | Ability to add app node during payroll peaks
| Monitoring | CPU, RAM, disk, DB performance monitoring

## API Integration Requirments
1. API Documentation
API definition / technical documentation relevant to payroll or salary data
2. Connection Parameters
Please provide the following for both Sandbox and Production (if applicable):
Base URL
Authentication method
API Key / OAuth 2.0 / Basic Authentication
Credentials or test access tokens
Required request headers
IP allow-listing / whitelisting requirements (if any)
Rate limits or throttling rules
3. Authentication & API Call Example
A minimal working example demonstrating:
How authentication is performed
How to call at least one key salary-related endpoint
4. Sample Payloads
Example request payload(s)
Example response payload(s)
5. MOST IMPORTANT – Salary Component Mapping
For each salary Excel template, please share the following details as per the attached Excel format:
API endpoint used for the salary data
API field name corresponding to each salary component
Mapping of API field name → Excel column,
strictly following the structure shown in Row 21 onwards of the attached Excel
This mapping is required for all salary components across all salary Excel templates to ensure accurate and consistent salary processing.

## Role Matrix
System Functions | Super Admin |  | Admin |  | C&B Staff |  | HR Manager |  | Chief Accountant |  | General Manager |  | Employee |  | Data Access | Data Action (CRUD)
| Access | Action | Access | Action | Access | Action | Access | Action | Access | Action | Access | Action | Access | Action
System Configurations | All Data | Edit | My BU | Edit | No Data | Edit | [8 empty] | No Data | View | Read
Attendance | All Data | Edit | My BU | Edit | My BU | Edit | [8 empty] | My Data | Edit | Create/Update/Delete
Payroll Config | All Data | Edit | My BU | Edit | My BU | View | [8 empty] | My BU Data
Payroll | All Data | Edit | My BU | Edit | My BU | Edit | [8 empty] | All Data
Approval | All Data | Edit | My BU | Edit | My BU | Edit
Pay Salary | All Data | Edit | My BU | Edit | My BU | Edit
Gov Reports | All Data | Edit | My BU | Edit | My BU | Edit
Analytics | All Data | Edit | My BU | Edit | My BU | View

## Approval Matrix
BU | Step 1 | Step 2 | Step 3 | Step 4
VPTQ | HR Manager | Account | General Manager
Logistics
Automibiles
Agri
...

## Templates Requirments
Templates
Employee Master Template
Personal & Statutory Details Template
Bank & Payment Details Template
Salary Structure / Compensation Template
Attendance & Leave Template
Overtime / Shift Allowance Template
Variable Pay / Incentive Template
Reimbursement Template
Deductions & Recoveries Template
New Joiner Template
Exit / Full & Final Settlement Template
Payroll Approval & Sign-off Template
Payslip Template
Bank Transfer Statement Template
Statutory Compliance Report Template
Payroll Accounting / GL Posting Template
Cost Center Allocation Template
Retro / Arrear Adjustment Template
Payroll Reconciliation Template
Reports
Payroll Summary Report
Payroll Register (Employee-wise)
Earnings & Deductions Report
Net Pay Report
Payslip Register
Attendance vs Payroll Variance Report
Overtime Cost Report
Variable Pay / Incentive Report
Reimbursement Payout Report
Deductions & Recoveries Report
Statutory Contributions Report
Tax Deduction Report
Social Insurance / PF / Pension Report
Cost Center-wise Payroll Cost Report
BU / Company-wise Payroll Report
New Joiner Payroll Report
Exit & Full & Final Settlement Report
Arrears / Retro Adjustment Report
Payroll Reconciliation Report (Month-on-Month)
Payroll Accounting / GL Posting Report
Payroll Dashboards
Payroll Overview Dashboard
Headcount & Payroll Cost Dashboard
Earnings vs Deductions Dashboard
Statutory Liability Dashboard
Cost Center / BU Payroll Dashboard
Overtime & Variable Pay Dashboard
Joiners vs Leavers Dashboard
Payroll Variance Dashboard
Compliance Status Dashboard
Payroll Processing Status Dashboard