## Tested and status
Ref | Area | What we need | Priority | Status | What we found | What needs to improve | Fix review / action required — 23 Oct 2026
REC-014 | Sourcing & Posting | Recruiter posts a role to multiple channels (LinkedIn, careers page, job boards) from one screen, each channel source-tagged for attribution. | High | Fail | Set up hiring › Channels lists 6 channels: Careers page, LinkedIn, JobStreet, VietnamWorks, Employee referrals, Agencies. Its own text says 'No job board is connected to this system'. For LinkedIn and VietnamWorks the Publish panel says 'Not connected… Paste the advert…'; the only options are 'Copy the advert' or emailing it to a board contact. There is no option to connect a board account. 'Add a channel' exists, but adds a tracked link, not a board connection. | MUST HAVE. Offer the job boards Rize has in Zoho Recruit (Job Opening › Publish › Job boards, incl. 'Yet to Activate'), each one Rize can switch on with its own board account. Send a board-by-board list: available now / built, waiting on Rize's account / not available yet + date. Confirm how applications made on a board's own site reach Payobook. | OPEN — integration required Careers page and tracked application links are available. LinkedIn, JobStreet and VietnamWorks have manual posting/email packs only; no API connector or board-native application import is built. Referrals and agency submissions use Payobook forms. Rize: provide the full Zoho board list and each account/API entitlement. Payobook: agree connector scope and delivery dates; no date is committed. Credentials alone will not activate an unbuilt connector.
REC-016 | Interviews & Feedback | Recruiter schedules interviews; invites + calendar holds go to candidate, interviewer and recruiter with agenda and video link; time zones auto-adjust across IN/VN/ID/SG. | High | Fail | 'Arrange an interview' asks you to type a date and time and pick the panel by name; it does not show anyone's availability or suggest slots. Set up hiring › Who does what says Google Calendar is not set up yet and an administrator must paste a Google client id and secret. Its description covers adding interviews to the recruiter's calendar and creating Meet links; it says nothing about reading availability. I saw no Outlook option. (A Calendly link is sent automatically for the recruiter screen, see CALL-03.) | Show panel availability and suggest slots (spec asks for free/busy and two-way sync). Self-scheduling for panel rounds, not only the recruiter screen. Confirm time zones are shown to each person. Confirm whether Rize IT must create Google credentials or can just approve Payobook's app. | PARTIAL — code deployed / calendar setup required Added official Google/Microsoft SDK panel free/busy checks, expiring single-use candidate booking, browser timezone selection and a fresh conflict check before booking. Native calendar time changes create an interview audit trail. Automated booking and reschedule tests pass. Chrome verified the booking form preserves the existing Asia/Calcutta timezone alias. Rize IT: configure OAuth applications, tenant consent and panel-calendar permissions; each organiser connects their calendar. Payobook/Rize: complete a controlled Google and Outlook booking/sync test. No live provider consent or availability is claimed.
REC-027 | Selection, Offer & Closure | On signed offer, the position auto-closes; HM and TA Lead notified; remaining candidates auto-move to Archived/Future-fit; onboarding pre-trigger fires. | Medium | Fail | DEMO Territory Manager shows '2 openings · 2 filled' and is still open with 16 people in play. Settings › Access describes 'closing a role and marking one filled' as a Talent lead action, so closing seems to be manual. | Spec (REC-027) asks for the role to close automatically when filled, with the HM and TA Lead told and remaining candidates archived. Do this when the last opening is filled, or at least prompt the Talent lead. | PARTIAL — code fixed / switches off The final signed offer now closes the role, stops referrals and unpublishes its careers advert. Remaining candidates without a live offer move to On hold with Future-fit status. Hiring manager, recruiter manager and Talent leads are included in closure notification recipients. Signed candidates remain candidates until Confirm they joined. The reported DEMO Territory Manager role is reconciled on payobook. Candidate test emails remain disabled. The existing demo auto-close and closure-email switches remain off. TA Lead: enable future-fit automation in Set up hiring > Automations; enable closure mail only after sender verification. The named demo repair is applied once even while that switch is off.
MH-03 | Hiring & Recruitment › Job Posting | Posting templates; publishing to LinkedIn and job portals from the portal. |  | Fail | Same as REC-014. | Same as REC-014. This was a must-have in the original list. | OPEN — integration required Same dependency as REC-014: direct job-board publishing and board-native application ingestion are not built. Manual posting with a source-tagged application link remains available. Rize must provide its board inventory and API entitlements; Payobook must agree and deliver each connector. No unsupported activation or delivery date is claimed.
MH-06 | Hiring & Recruitment › Closure Notification | Once signed, the position is marked closed; hiring manager and recruiter's manager notified. |  | Fail | Same as REC-027. | Same as REC-027. | PARTIAL — code fixed / mail setup Same fix as REC-027: close automatically when signed/joined offers cover the last opening; notify hiring manager, recruiter manager and Talent leads. The candidate becomes an employee only after Confirm they joined. Email delivery requires the approved sender setup. Demo closure mail is currently off; TA Lead must enable it after sender verification. No delivery was claimed.
RIZE-01 | Platform › Access | TA users (Recruiter, Talent lead) can see and do hiring only. No access to HRMS screens (payroll, employee records, budgets, compliance, bank verification) and no way to change anything there or see who holds HR/payroll roles. |  | Fail | With the Talent lead login: Settings › Access lists all 67 roles across Payroll, People, Money & budgets, System and Lifecycle, with the names of the people who hold each (e.g. 'Payobook' holds 'Joiners and leavers'), plus 'Who holds what' and 'Hand my access over' buttons. The search bar offers Workforce, Compliance, Bank Verification, Pulse, Approvals, Dashboard and Inbox as well as Hiring. Settings › System not checked. I didn't try to open or change anything on the HRMS side, so I can't say whether it's view-only or editable. The demo may use a broad 'Demo login' role, which could explain some of this. | In Rize's setup, TA users get hiring screens only: no HRMS screens in search or menus, no view of the Access screen or who holds HR/payroll roles, and no ability to change HR settings. Confirm in writing which permissions the Recruiter and Talent lead roles carry, and show it with a login set up exactly as Rize's TA team will have it. | PARTIAL — access setup required Added Hiring only profile: unrelated sidebar/search entries and the Access directory are hidden; server access to that directory and its role catalogue is refused. Applied to the two demo TA logins. Recruiter handles candidates; Talent lead additionally manages hiring setup, country rules and retention. Rize administrator: assign this profile with the appropriate hiring role to real TA users, remove independent HR/payroll/admin grants, and complete negative-access tests. This profile does not revoke separately granted permissions. Deployed Chrome/API checks passed for both demo roles; Recruiter sees hiring rules read-only and cannot load connection settings.
REC-005 | Platform, Access & Config | The online candidate application form must be fully editable: add, remove, reorder and rename fields, add custom questions, and apply Rize branding, without vendor intervention. | Critical | Partial | The application form opens and shows correctly (I didn't submit one). The careers page and form show Payobook's logo, phone and 'Contact Us' on payobook.com. As Talent lead I found nowhere to change this: Settings only has 'Access & delegation', and searching 'career' or 'website' finds nothing. Form questions are editable under Set up hiring › Application forms. | Show us where Rize's branding and careers page are set (logo, colours, About Rize, contact details), and let the TA Lead change it. Careers page on a Rize domain. | MANUAL — website administrator The application-form editor remains available. A website administrator can configure careers logo, colours, company text, contact details and domain using existing website tools; no dedicated TA branding editor was added. Rize supplies approved assets, legal entities and hostname; IT verifies DNS/HTTPS. Keep shared payobook.com demo branding separate from the Rize production site. This is accepted manual configuration, not a missing mandatory provider integration.
REC-007 | Platform, Access & Config | Different role types and countries must use their own stage sets (pipelines), editable by the TA Lead role-by-role without raising a request. | Critical | Partial | Stages come from one shared list of 17 that the Talent lead can rename and reorder. A single role can hide columns ('1 hidden for this role'). Presets per department/country exist but none are set up ('0 presets'), so I couldn't check roles running different pipelines. | Set up 2–3 presets (e.g. field, tech, commercial) in the demo so we can test this. | FIXED — retest Added DEMO Field roles, DEMO Tech roles and DEMO Commercial roles under Set up hiring > Presets in the demo Talent lead's company. Each has a distinct stage selection; existing customer pipelines are preserved. TA Lead: assign a preset by department/country or choose the columns on an individual role, then create separate sample roles to compare them.
REC-008 | Platform, Access & Config | Access and field visibility must be controllable by role at each stage (e.g. salary/offer visible only to Recruiter, HM, HR; resume bank hidden from Hiring Managers; panel feedback hidden between interviewers until all submitted). | Critical | Partial | Who sees a candidate is set per candidate with 'Share with…' (profile, CV, portfolio, answers, scorecards, expected pay). Settings › Access lists roles and what each opens; for hiring it has only Recruiter, Talent lead and Head of hiring. I found no setting for what HMs, interviewers, Finance or agencies see at each stage. HM view not checked. | A setting the TA Lead controls for what each group sees at each stage (spec REC-008), so it doesn't depend on sharing person by person. | PARTIAL — policy code deployed / configure matrix Added company-scoped stage visibility policies for the hiring manager, interview panel and named groups with existing role access. Matching policies control profile, CV, portfolio, assignments, attachments, answers, scorecards and expected pay. Downloads recheck access and obsolete bearer links are invalidated. Automated access tests pass; agency restrictions remain. Rize TA Lead: approve and configure the stage/audience matrix in Hiring connections > Stage visibility, then test real HM/panel/Finance/agency accounts.
REC-035 | Platform, Access & Config | The workflow must be non-blocking: no approval gate or system lock may stop a record from progressing at any stage. Approvals are recorded and notified for audit but never halt movement. Recruiters have full access to move requisitions and candidates through any stage. All automations and customisations (stages, forms, templates, rules) are owned and self-served by the TA Lead. | Critical | Partial | Moving cards isn't blocked. Settings › Access says the hiring rules (who recruits for which country) belong to 'Head of hiring'; the Talent lead login can open Settings › HR › Hiring rules, but I didn't try editing. The data clean-up says 'Running the clean-up is for the head of hiring'. Google Calendar keys are pasted by an administrator. Also see REC-023: the background check text suggests it blocks the offer. | Let the TA Lead own hiring rules and clean-up, as REC-035 asks. | FIXED — retest Talent lead can now create/edit country hiring rules and control retention clean-up; Recruiter cannot change these controls. Hiring rules is available in search to Talent lead. Background checks do not block offer drafting. The established agreed-request check before sending an offer remains. No retention deletion or nightly clean-up was run as part of this review.
REC-030 | Sourcing & Posting | Agency-run roles are tagged; agencies submit candidates via a limited portal (submit only — no internal notes, comp or other candidates); internal recruiter owns all communication; vendor performance tracked. | Medium | Partial | Agency portal and the 6-month rule exist (agency sign-in not checked). In Hiring numbers, 'An agency, or our own team' shows 'With an agency: 2 of 2 filled' and 'Our own team: 0 of 19', while the agency table shows DEMO Talent Bridge with 0 joined. On DEMO Territory Manager (which has an agency) the two joiners came via JobStreet and LinkedIn. It looks like a role counts as agency-filled just because an agency is on it. | Count a fill for the agency only when the agency's candidate joins. | FIXED — retest Agency/internal figures now count joined candidates by the candidate's actual submitting agency. Attaching an agency to a role no longer credits it for a direct hire. Days run from role opening to actual joining; the screen and export labels now say Candidates and Joined. The individual agency table's timing also follows its own joined candidates.
REC-015 | Screening & Talent Pool | Recruiter screens and tags each applicant (Shortlisted / Rejected / Future-fit / Fit for other role); tagged candidates flow into a searchable internal Resume Bank visible only to Recruiter/TA/HR. | High | Partial | Resume bank has filters for skill, country, team, tag and source, and is hidden from HMs per their matrix (HM view not checked). But skills come only from tags added by hand: 9 of the 10 people found had 'No skills or tags yet'. Searching 'agronomist' returned only people whose last role title contains 'Agronomist'. Profiles show no details taken from the CV. (Demo CVs may be placeholders, so this needs confirming.) | Confirm whether CVs are parsed. If not, fill skills/experience from the CV so search works without tagging every person by hand. Confirm whether search looks inside CV text. | PARTIAL — parser built / hosting and acceptance pending Added a Docling + spaCy service, OCR, configured-skill matching and reviewable employment/education text. New CVs queue when enabled; existing CVs use Extract CV. Reviewed suggestions preserve existing manual history unless replacement is selected; extracted text is indexed. Synthetic PDF, DOCX and scanned-image checks are reported in the release notes. Required: approve a service host, deploy/test its Linux container, enter its URL/key, then test representative English/Vietnamese/Indonesian CVs. Employer/title/year normalization and inferred skill proficiency are not implemented.
REC-019 | Interviews & Feedback | Every interview must be closed with an outcome: Attended / Candidate no-show / Interviewer no-show; candidate cannot advance until logged. | Medium | Partial | 'Outcome to log' prompts exist. But Ly Thi Thu is marked Joined while her Round 2 interview is still 'Arranged', and Round 1 still waits on an opinion. | When a candidate moves on, joins or is closed, open interviews must be closed or flagged, not left hanging. | FIXED — retest A joined/closed candidate with an overdue interview still shows Outcome to log. Progress remains non-blocking and no attendance or no-show result is invented. Recruiter must record the actual interview outcome and complete outstanding feedback; existing arranged interviews are not silently marked attended.
REC-020 | Interviews & Feedback | Each panellist submits structured feedback within 24 working hours; reminder on breach; escalation to TA Lead if still missing. Feedback hidden between panellists until all submitted. | High | Partial | Late opinions are chased, and the built-in rule tells the talent lead at 2 days late. 'Opinions late' shows 10 on the Applicants board but 0 in the summary bar at the top of the Hiring screen. The spec's notification table says escalate at 24 working hours. | Make the late-opinion counts agree. Escalate to the TA Lead at 24 working hours. | PARTIAL — code fixed / chase off The top summary counts candidates with late feedback across all rounds, matching the Applicants late-opinion count; older outstanding interviews remain visible beyond the recent-interview window. Default Talent lead escalation now occurs when the 24-working-hour feedback deadline passes, rather than two further days later. Working hours use the company's calendar. Explicitly customized non-default delays are preserved; TA Lead should review them. The demo chase switch remains off. TA Lead: enable feedback chasing after the approved mail-delivery setup/test; no live escalation email was sent in this review. Deployed check: both the overview API and Applicants screen report 6 late candidates.
REC-023 | Selection, Offer & Closure | Manual BGV via calls against a defined template with document upload; runs in parallel and is recorded, but does NOT lock offer preparation. | High | Partial | Settings › HR › 'What a background check covers' says: 'Each line has to be answered before an offer can be drafted.' That would block the offer, which goes against the spec and their own matrix comment ('never blocks it'). Not tried. | Background check must run alongside the offer and never stop it being drafted (REC-023, REC-035). Confirm and fix the wording or the rule. | FIXED — retest Confirmed offer drafting is permitted with unanswered background-check lines. Corrected the setup wording: the check runs alongside the offer and does not block drafting. The agreed hiring request remains the separate prerequisite before sending an offer. Retest by opening a draft with an unfinished BGV checklist.
REC-025 | Selection, Offer & Closure | Recruiter prepares country-specific salary file; HM and HR/Finance sign-off is recorded and notified but non-blocking - the recruiter can progress. Compensation fields visible only to authorised roles. | High | Partial | Per their matrix, the offer has pay lines with totals; country offer templates and letters come later. I didn't open the offer screen. | Country offer templates and a salary calculator (spec). Suggestion: use Payobook's payroll rules to show employer cost and statutory contributions per country. | PARTIAL — calculator deployed / Finance configuration Added explicit company/country/effective-date offer profiles using Payobook payroll formulas for employer-cost estimates. Required inputs cannot silently default to zero; monthly, annual and first-year one-time costs are separate. Pay changes invalidate estimates. Automated calculation tests pass. Rize HR/Finance: approve the payroll configuration, input/output mappings, defaults/rates, country letter and counter-signatory; administrator enters these in Country offer setup. No statutory rates were invented and estimates do not post payroll.
REC-026 | Selection, Offer & Closure | Approved offer sent for e-signature (DocuSign / Zoho Sign); signed copy auto-filed; multi-country routing supported. | High | Partial | Per their matrix: offers are signed outside the system and signed copies are uploaded by hand. | Generated offer letters per country and e-signature, with a committed date. | PARTIAL — DocuSign coded / account activation pending Replaced new-offer signing with DocuSign: company-scoped encrypted JWT credentials, draft creation/recovery, reviewed signer and required-signature checks, send/void/restart, HMAC callbacks, API-verified completion and signed-PDF filing including the completion certificate. Twelve DocuSign regression tests pass with mocked provider responses. Required: DocuSign eSignature API entitlement, integration/user/account IDs, RSA key, sender consent and account Connect HMAC key. Run a controlled live signing/archive test before acceptance. No self-hosted signing server is required; existing legacy envelopes retain their original provider.
REC-033 | Selection, Offer & Closure | Application must capture explicit candidate consent for data processing/retention; retention period and deletion rules configurable per market. | High | Partial | The form has a consent tick in the candidate's language; in the demo it names 'Payobook Vietnam JSC'. Retention months are set per country. Clean-up is off and 'Running the clean-up is for the head of hiring'. | Consent text must name the right Rize entity per country. Tell us where candidate data is hosted, how candidates ask for access/deletion, and who at Payobook can see candidate data. Let the TA Lead run clean-up. | PARTIAL — privacy setup required Talent lead now owns retention controls. Clean-up was not executed or enabled. Rize must approve the correct legal entity/consent text and retention period per country. Payobook owner must supply confirmed hosting location, candidate access/deletion request contact/process, and staff/support access list. The shared demo's Payobook entity is not a verified Rize production consent statement.
REC-029 | Analytics & Reporting | Track time to fill, time to offer, time in stage, offer acceptance rate, source effectiveness, and internal/external delay split; filterable and exportable. | High | Partial | Hiring numbers covers time to fill, time to offer, time in stage, offer → joined, sources, interview moves, agencies and longest-waiting, with filters and Excel download (download not tried). Issues: the agency count above (REC-030); 25% of candidates have source 'Not recorded'; late-opinion counts differ (REC-020). | Fix the agency count. Make source required so 'Not recorded' doesn't happen. Tell us when the time-to-fill clock starts (role opened, or request agreed). | PARTIAL — historic source review Fixed agency attribution and late-feedback counts. New direct careers applications get Careers page; internal additions/imports get Manual entry / import unless a specific source is supplied. Existing unknown sources are preserved rather than guessed. Recruiter: correct historical sources from evidence and choose specific sources for imports. Time-to-fill uses opened_on to filled_on (role opening to final signature after this fix), not request agreement; agency joining time is labelled separately.
MH-05 | Hiring & Recruitment › Offer Preparation | Salary file → hiring manager review → final offer draft → candidate review. Country-wise offer templates; salary calculator; approval workflow. |  | Partial | Pay lines built; country offer templates and letters 'follow later'. | Same as REC-025 / REC-026. | PARTIAL — code deployed / setup and provider test Country employer-cost calculation, explicit letter/signatory setup and DocuSign signing integration are coded; see REC-025/026. HR/Finance approves country formulas, rates, letters and signers. Administrator configures profiles and DocuSign API account/consent/keys. A controlled live signing/archive test remains pending. No custom signing server is needed.
CALL-01 | Platform | A simpler Hiring screen with fewer filters. |  | Partial | The Hiring screen is simpler. Input boxes are near-black with low-contrast text, so values are hard to read (e.g. 'Open a role': Department, Country, seats, recruiter). Placeholder text like 'Territory Manager' looks like a filled-in value. The Rize TA Lead couldn't use the form because of this. | Readable contrast on all inputs (or a light theme), placeholders that look like hints, and required fields marked with *. | FIXED — retest Corrected hiring-modal colour inheritance so dark inputs and text use the same palette. Placeholders use subdued italic hint text; the role-title example now says For example. Required role title and department are marked *. Retest Open a role in light and dark appearance and confirm actual selected values remain readable. Live Chrome confirmed readable light-mode fields and saved a DEMO role. Dark appearance remains a client retest: this session exposed no appearance switch.
CALL-02 | Requisition | A role can exist before, or without, a hiring request. |  | Partial | Opening a role works: I created 'DEMO Rize test role - delete' with the Talent lead login. Leaving title or department empty shows 'Complete the required fields'. The Rize TA Lead couldn't open a role because the fields couldn't be read (CALL-01). | Fix as CALL-01. | FIXED — retest Uses the CALL-01 contrast and required-field fixes. A role can still be opened before requesting manager agreement. Retest with a clearly named DEMO role; title and department are required. The client's existing test role was not deleted. Live Chrome saved DEMO Client Review QA 23 Oct successfully; the QA role was registered and closed after testing.
CALL-11 | Analytics | Offer-drop measurement: offered → accepted → joined. |  | Partial | Offer → accepted → signed → joined funnel shows in Hiring numbers. | Same data checks as REC-029. | PARTIAL — data review The offered > accepted > signed > joined funnel remains. Agency attribution is corrected as in REC-030. Historical unknown sources still require evidence-based correction (REC-029). Rize should reconcile the funnel against a small agreed set of real offers before acceptance; no historical outcomes have been fabricated.
CALL-07 | Communications | Emails go out from Rize's own address (@rize.farm). |  | Rize action | In the demo, emails are set to go from "Payobook Vietnam JSC" <ash@biztinct.com>. | Send Rize the records to add to rize.farm before go-live. | MANUAL — Rize IT and Payobook Rize must choose/authorize its outbound mail provider and sender address. Payobook must then provide that provider's exact SPF, DKIM and return-path records; Rize IT adds them and agrees the DMARC policy. Those values cannot be safely invented without the chosen provider/account. After verification, configure the Rize company sender and test delivery to an agreed test inbox before enabling candidate emails.
REC-036 | Platform, Access & Config | The candidate application form must support multiple languages. A form (or a language version of a form) can be created in Bahasa Indonesia, Vietnamese, English, etc., and the candidate sees the form in the appropriate market language. | High | Pass | English / Tiếng Việt / Bahasa Indonesia switch on the candidate form. | None. | CLIENT PASS — retained Client's multilingual-form pass is preserved. No change requested. Include English, Vietnamese and Bahasa Indonesia in the next application-submission acceptance test; labels alone do not verify delivery or submitted data.
REC-006 | Platform, Access & Config | Each job must show candidates on a drag-and-drop Kanban board, with columns = stages, and cards moved between stages by dragging. | Critical | Pass | Board per role works, with counts per column. | Set the stage order to Rize's process before testing (it can be changed in Set up hiring › Stages). | MANUAL — TA Lead Client's Kanban pass is preserved. TA Lead should set the agreed stage order in Set up hiring > Stages and choose the new presets for sample roles (REC-007). The review does not overwrite the client's chosen shared stage order.
REC-010 | Requisition & JD | MR budget is verified and flagged; over/unfunded budget notifies Finance + HM's manager for an audit trail but does NOT block the requisition from progressing (non-blocking). | High | Pass | 'Over budget' counter shows on the Hiring screen (3 roles). Set up hiring › Who does what has a list of who is told; in the demo it's only DEMO Talent Lead. | At setup, add Finance, HM's manager, CEO, Head of HR and TA Lead to the list. | MANUAL — Rize administrator Client's non-blocking budget pass is preserved. Configure the approved Finance, HM manager, CEO, Head of HR and TA Lead notification recipients in hiring setup. Real identities/recipients were not guessed and no test notifications were sent to them.
REC-001 | Screening & Talent Pool | Candidate must provide expected salary during application where requested. | High | Pass | Expected monthly pay is a required question on the form (VND for a Vietnam role). | Check the currency changes with the role's country. | CODE REVIEW — client retest The application page derives the expected-pay currency from the role's country, falling back to the company currency. No fix was needed. Retest one role each in India, Vietnam, Indonesia and Singapore and confirm INR, VND, IDR and SGD on both the form and saved answer.
REC-002 | Screening & Talent Pool | Candidate must provide portfolio where applicable. | High | Pass | Portfolio field on the form (file or link). |  | CLIENT PASS — retained Client's portfolio field pass is preserved. No code change requested. A later submission test should include a valid file and a URL where that role's form allows them.
REC-003 | Screening & Talent Pool | Define the initial screening mechanism and responsible role. | Critical | Pass | 'First look' tags show on new cards. |  | CLIENT PASS — retained Client's First look screening pass is preserved. No change requested.
REC-004 | Screening & Talent Pool | Recruiter should be able to identify when a candidate applied and view the candidate timeline. | High | Pass | Cards show 'Applied X days ago · source'; profile shows applied date. |  | CLIENT PASS — retained Client's application date/timeline pass is preserved. No change requested.
REC-031 | Screening & Talent Pool | Each candidate must have a visible activity timeline (applied date, stage changes, interviews, emails, notes) accessible from the profile. | Medium | Pass | Timeline on the profile shows applied, moves and emails sent. |  | CLIENT PASS — retained Client's activity timeline pass is preserved. No change requested.
REC-037 | Interviews & Feedback | Recruiters need a dedicated space to write their own interview notes on a candidate. These notes are private - visible only to the TA Lead (and the recruiter who wrote them), and not to hiring managers, interviewers, or other recruiters. | High | Pass | Private 'Recruiter notes' section on the profile, kept off the timeline. |  | CLIENT PASS — retained Client's private recruiter-notes pass is preserved. No permissions were broadened for these notes. Include a second recruiter and interviewer login in the final privacy acceptance test.
REC-032 | Communications | All automated emails must use editable templates managed by HR, with multi-language support for ID/VN/IN/SG. | Medium | Pass | 16 candidate emails listed, each with EN / VI / ID versions. Editing and delivery not tried (candidate emails are switched off in the demo). | Test delivery once candidate emails are switched on. | MANUAL — delivery test pending Client verified the editable multilingual template list, not delivery. Candidate emails remain disabled in the demo. After CALL-07 sender verification, enable mail only for an agreed controlled test and verify EN/VI/ID delivery and reply-to before go-live.
CALL-03 | Interviews | Moving someone to “Recruiter review” sends the recruiter's Calendly link automatically. |  | Pass | Rule 'enters Recruiter review → send Let's chat' has run. |  | CLIENT PASS — retained Client observed the Recruiter review > Let's chat rule run. No change requested. Real recruiters must supply their own working scheduling links; the demo link is not a production booking calendar.
CALL-06 | Communications | Email automations the talent lead sets up herself. |  | Pass | 'Add a rule', 'Try it on a candidate' and 'What ran' all present. |  | CLIENT PASS — retained Client's automation-editor pass is preserved. No change requested. The feedback escalation built-in now describes the corrected deadline behavior (REC-020).
Colour guide — original client results are unchanged
GREEN: Code fix deployed and checked; client acceptance retest remains.
RED: Requirement remains open; implementation/integration is required.
AMBER: Partial fix, manual setup or an unresolved policy decision.
BLUE: Not client-tested / code review only. No client Pass is claimed.
GREY: Existing client Pass retained; no new acceptance claim.
Release f7cd70ae0 (DocuSign). pb_hiring 19.0.2.13.0; pb_hub 19.0.1.12.2. Deployed: payobook, payobook_template, p0clone, rize. 42 recruitment regression tests passed, including 12 DocuSign tests. Deployed Chrome setup/offer controls and role/API checks passed. Six earlier CV-service tests passed. DocuSign demo account creation, credentials, consent and live signing/archive test remain pending; CV hosting is unchanged.

## Yet to be tested
Ref | Area | What we need | Priority | Sign in as | How to test it | Tested by | Result (Pass / Partial / Fail) | Notes | Fix review / action required — 23 Oct 2026
REC-028 | Platform, Access & Config | When a recruiter is unavailable, their open requisitions can be delegated to a backup for a date range, approved by TA Lead, logged, and auto-reverted at end date. | Medium | Recruiter | 1. Sign in as the Recruiter. 2. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 3. Press “Hiring tools” › “Cover for me”. 4. Choose the colleague, the dates and the reason, then send it. 5. “Hiring tools” › “Covers” shows who is covering for whom. |  |  | Approver must be the TA Lead (spec), not only the recruiter's manager. Confirm who approves when the TA Lead is the one on leave (Head of HR). | NOT CLIENT-TESTED — Added explicit TA Lead and Head of HR fallback with dated absence handling; self-approval is blocked and no org-chart fallback is assumed. Automated routing tests pass. Fixed access to existing rule forms; Chrome verified the named approver and absence-date fields. Rize TA Lead/administrator: configure the named approvers per country, then test normal approval, lead absence, requester-is-lead and cover reversion. Client test-result cells remain unchanged.
REC-009 | Requisition & JD | Only Hiring Managers can raise a Manpower Requisition using the standard MR form with all mandatory fields. | High | Hiring manager | 1. Sign in as the Hiring manager. 2. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring”. 3. Press “Raise a hiring request”. 4. Fill in each step: role, department, country, reason, how many, reporting manager, the interview rounds, budget, target date. Send it. 5. The Confidential switch is on the role: Open the “Details” tab of the role › “Request & role” › “Confidential”. |  |  | Needs the Hiring manager sign-in. | NOT CLIENT-TESTED — Use a Hiring manager login to submit the standard request and exercise missing required fields. Recruiter/Talent lead Open a role is a separate permitted flow before an agreed request. Role-title and department readability/required markers were corrected in CALL-01.
REC-034 | Requisition & JD | Recruiter can initiate a Manpower Requisition request and assign it to the Hiring Manager to complete the mandatory details - whether the role is not yet opened or already open - and can send reminders to the HM until it is completed. | High | Recruiter / Hiring manager | 1. Sign in as the Recruiter. 2. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 3. Press “Ask a manager for a request”, fill in the role and choose the manager, then send it. 4. The manager gets one page by email (no sign-in needed). It saves as they type; sending it in is their agreement. 5. To nudge them yourself: press “Remind now” on the role's row. |  |  | Needs the Recruiter and Hiring manager sign-ins. | NOT CLIENT-TESTED — Exercise Ask a manager for a request, manager token-page save/submit, then Remind now using controlled test recipients. Email delivery requires the verified sender setup. No client Pass has been inferred from the existing implementation.
REC-011 | Requisition & JD | On budget approval, the recruiter for the role's country and the TA Lead are notified and the MR is auto-assigned. | High | Head of hiring | 1. The country-to-recruiter list: search bar › type “hiring rules” › open “Hiring rules” (Head of hiring). 2. On the Hiring screen each role row shows who recruits it (for example “DEMO Recruiter recruits”). |  |  | Yes, copy the TA Lead on every assignment. Give the TA Lead access to 'Hiring rules'. | NOT CLIENT-TESTED — Assignment notices now include the country rule’s designated TA Lead, deduplicated with recruiter/manager recipients. Configure real country recruiter and TA Lead identities, then approve a controlled request and verify assignment and both inboxes after mail verification. Existing notification switches remain unchanged.
REC-012 | Requisition & JD | Recruiter drafts JD from a template and shares the draft with the Hiring Manager for input; the final JD is versioned (not locked) and stored in a central repository linked to the MR. No formal HM approval gate - JD is discussed with the HM separately. | High | Recruiter | 1. Sign in as the Recruiter. 2. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 3. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 4. Open the “Details” tab of the role › “Advert & publishing” › “The advert”. 5. Choose “From a template…” (Field roles, Sales roles, Tech roles, Finance roles) and press “Start”, or “Write one”. 6. Share it with the manager for comments, then make it final. Older versions stay readable. |  |  |  | NOT CLIENT-TESTED — Exercise template > share draft > manager comment > final version and verify older versions remain readable. Current recruitment requirement specifies discussion/versioning without a formal HM approval gate; agree this interpretation against MH-02 before signing off.
REC-013 | Sourcing & Posting | On JD finalization, the role auto-opens for employee referrals unless flagged Confidential (sensitive/replacement). | Medium | Any employee / Recruiter | 1. Sign in with any demo login and go to payobook.com/my/refer. 2. Press “Refer for this role” next to a role and fill in the short form. 3. Recruiter: on the role, Open the “Details” tab of the role › bottom of the page › “Close to referrals” to stop referrals. |  |  |  | NOT CLIENT-TESTED — Finalize one ordinary and one confidential sample advert; verify only the ordinary role is available for employee referrals. Retest that a fully filled role is closed to referrals after REC-027.
REC-017 | Interviews & Feedback | Automatic reminders 24 hours and 30 minutes before each interview to all parties (email; SMS optional). | Medium | Automatic | 1. Nothing to press: the day-before and 30-minute reminders go by themselves. 2. To switch them off: Talent lead › “Set up hiring” › “Automations” › the built-in list. |  |  | Spec: email, SMS optional. Suggestion: WhatsApp, since email alone may not reach field candidates. | NOT CLIENT-TESTED / MANUAL ACTIVATION — Added optional Meta WhatsApp template reminders, explicit candidate consent, queued delivery and signed delivery-status callbacks. Automated consent/deduplication tests pass; email reminders retain existing SMTP/OAuth. Rize must supply verified WABA/phone, approved four-parameter template, token/app secret and controlled test recipient opt-in. Check and enable in Hiring connections, then verify day-before and 30-minute delivery. No SMS connector or live WhatsApp delivery is claimed.
REC-018 | Interviews & Feedback | Reschedules require ≥30-min notice, a mandatory reason, and a delay tag (Internal / External); old and new times logged. | Medium | Recruiter | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 3. Open the “Interviews” tab of the role. 4. Press “Move it” on the interview, pick the new time, give the reason and say whose side moved it. |  |  | 'Move it' and 'Nobody came' buttons are on each interview. | NOT CLIENT-TESTED / RULE DECISION — Existing behavior records short notice and reason/delay attribution without imposing a hard progression gate. Test Move it and the old/new time log. Confirm whether 30-minute notice/reason should remain warnings, given REC-035's non-blocking requirement, before adding a conflicting hard block.
REC-021 | Interviews & Feedback | Recruiter advances candidate to the next round or sends a templated rejection; templates editable by HR. | Medium | Recruiter | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 3. On a card press “Advance”, or “Not this time”. 4. “Not this time” asks CV reject or Interview reject, and has a tick for “send the email”. 5. The email words: Talent lead › “Set up hiring” › “Emails and languages”. |  |  |  | NOT CLIENT-TESTED — Test Advance and both rejection categories with controlled recipients. Verify HR-editable email text and the send-email switch; delivery is pending verified sender setup.
REC-022 | Selection, Offer & Closure | Panel debrief for finalists with side-by-side scores; final decision recorded (Selected / Not selected / Hold); selecting one flags others for archive/future-fit. | High | Recruiter / Hiring manager | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. Open a role that has finalists (for example DEMO Site Agronomist › “Review candidates”). 3. Press “Compare finalists” at the top: every scorecard side by side. 4. For each person press “Choose”, “Keep warm” or “Not this time”. 5. Also on the role's “Interviews” tab: “Debrief”. |  |  |  | NOT CLIENT-TESTED — Exercise Compare finalists with completed panel scorecards and record Choose/Keep warm/Not this time. The new full-role behavior moves remaining candidates without live offers to Future-fit when the last opening is signed; it does not fabricate panel decisions.
REC-024 | Selection, Offer & Closure | On BGV clear, candidate is auto-emailed a secure upload link for documents with a 2-day deadline and reminders; recruiter sees a live checklist. | Medium | Recruiter / Candidate (no sign-in) | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 3. Open the “Details” tab of the role › “Offer & joining”. 4. Press the “Documents” step, then “Ask for their papers”. 5. The candidate gets a secure upload page by email; the checklist on the same step fills in as files arrive. |  |  | Spec asks for the request to go out automatically when the background check clears; their matrix says the recruiter presses a button. | NOT CLIENT-TESTED — Code already supports automatic document requests when BGV clears through the on_check_clear trigger, with a manual request button as an additional path. Check Set up hiring > Who does what, then clear a sample BGV and verify the token email, deadline and upload checklist end-to-end.
MH-01 | Hiring & Recruitment › MR Notification | Based on the selected country, the assigned recruiter and the recruiter's manager are notified (email + portal). |  | Recruiter / Head of hiring | 1. The country-to-recruiter list: search bar › type “hiring rules” › open “Hiring rules” (Head of hiring). 2. On the Hiring screen each role row shows who recruits it (for example “DEMO Recruiter recruits”). |  |  |  | NOT CLIENT-TESTED — Country rules now include a designated TA Lead in assignment notices alongside recruiter/manager. Configure the approved real recipients and perform a controlled request/assignment/inbox test; Talent lead can maintain these rules. No client Pass is inferred.
MH-02 | Hiring & Recruitment › JD Finalization | Recruiter drafts the JD, gets hiring manager approval and stores it in a central folder. |  | Recruiter | 1. Sign in as the Recruiter. 2. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 3. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 4. Open the “Details” tab of the role › “Advert & publishing” › “The advert”. 5. Choose “From a template…” (Field roles, Sales roles, Tech roles, Finance roles) and press “Start”, or “Write one”. 6. Share it with the manager for comments, then make it final. Older versions stay readable. |  |  |  | NOT CLIENT-TESTED / REQUIREMENT CONFLICT — This row requests HM approval, while REC-012 explicitly removes a formal JD approval gate. Current flow supports draft sharing, comments and versioned finalization. Rize must confirm the accepted interpretation before this row can pass.
MH-04 | Hiring & Recruitment › Background Verification | BGV required before the offer draft. |  | Recruiter | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 3. Open the “Details” tab of the role › “Offer & joining”. 4. Under “The offer”, press the “Background” step for the chosen person. 5. Fill in each check line and attach documents. |  |  |  | NOT CLIENT-TESTED / REQUIREMENT CONFLICT — This older row requires BGV before an offer draft; REC-023/REC-035 explicitly require parallel, non-blocking BGV. Regression testing covers draft creation with unfinished BGV. Rize should confirm that the newer non-blocking requirement supersedes this row.
MH-07 | Onboarding › Pre-Onboarding Trigger | When the offer is accepted and the position closed, the hiring manager is emailed to nominate buddies; pre-onboarding starts. |  | Recruiter / Hiring manager | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. Open DEMO Territory Manager › “Review candidates” › click Cao Minh Khoa. 3. “Before they join” lists: ask the hiring manager to name a buddy, ask the joiner for laptop preferences, set up a meet-the-team chat, send first-day details. 4. The hiring manager names the buddy from one email (no sign-in). 5. The standard list: Talent lead › “Set up hiring” › “Before they join”. |  |  |  | NOT CLIENT-TESTED — Sign a controlled sample offer and verify the manager buddy request and pre-joining checklist. Role closure now happens at the last signed opening. Confirm they joined remains the separate step that creates the employee.
MH-08 | Onboarding › Laptop Procurement | Laptop needs captured before joining (10–15 days before the date of joining). |  | Recruiter / Candidate (no sign-in) | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. Open DEMO Territory Manager › “Review candidates” › click Cao Minh Khoa. 3. “Before they join” › “Ask … for their laptop preferences” › “Remind them”. 4. The joiner answers on a page in their own language; the answer lands on their card. |  |  |  | NOT CLIENT-TESTED — Verify the laptop preference request/token answer and checklist update for a sample joiner. Confirm the approved 10–15-day timing against the configured pre-joining task offsets; a visible Remind them button alone is not proof of automatic timing.
CALL-04 | Selection | No offer without an agreed hiring request (the one hard rule). |  | Recruiter | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 2. On the “Roles” tab, find the role (for example DEMO Territory Manager) and press “Review candidates”. 3. Open the “Details” tab of the role › “Request & role”: “Request agreed” or who still has to press “Agree”. |  |  |  | NOT CLIENT-TESTED — The established hard rule is no offer sending without an agreed request. Offer drafting remains allowed. Test sending with an unagreed request, agree it, then repeat with a controlled candidate; no real offer should be sent during acceptance testing.
CALL-05 | Communications | Only Rize's own confirmation email goes out when someone applies. |  | Talent lead | 1. Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring”. 2. Press “Set up hiring” at the top of the Hiring screen. 3. “Emails and languages” › “Application received”. |  |  |  | NOT CLIENT-TESTED — Verify a controlled careers submission generates exactly one configured Application received email. Review its sender and language. Candidate mail remains disabled in the demo pending the approved delivery test.
CALL-08 | Joining | The person stays a candidate, with the recruiter, until the date of joining is confirmed. |  | Recruiter | 1. Nothing to press when the offer is signed: the hiring manager and talent lead are told and the “Before they join” list starts. 2. To see it: Open Hiring: click the search bar at the top of the screen (or press Ctrl+K / ⌘K), type “hiring” and choose “Who we are hiring” (Recruiters can also use the left menu: Operate › Lifecycle.) 3. Open DEMO Territory Manager › “Review candidates” › click Cao Minh Khoa. 4. “Before they join”: buddy, laptop preferences, meet-the-team chat, first-day details. 5. On the first day press “Confirm they joined” (this creates the employee), or “Did not join” with a reason. |  |  |  | CODE REGRESSION COVERED / CLIENT RETEST — Final-signature closure does not create an employee. Confirm they joined still controls employee creation; Did not join records the drop. Client must exercise both branches on sample candidates before acceptance.
CALL-09 | Joining | Pre-onboarding run by the recruiter: buddy, laptop preferences, meet-the-team chats. |  | Recruiter | (same as MH-07) |  |  |  | NOT CLIENT-TESTED — As MH-07, verify buddy, laptop preferences and meet-the-team tasks remain with the recruiter while the person is a candidate. Test each token response and due-date behavior.
CALL-10 | Joining | Reminder one week before the expected joining date to recruiter, hiring manager and HR. |  | Automatic | 1. Nothing to press: one email a week before the date (still on, date changed, or not joining). 2. On the person's card you can also press “Send the “still on?” email now”. 3. Switch: “Set up hiring” › “Automations”. |  |  |  | NOT CLIENT-TESTED — Test the one-week-before joining reminder with controlled dates/recipients, including changed date and not joining responses. Verify that the notification reaches recruiter, hiring manager and HR. A visible automation switch does not prove delivery.
Colour guide — original client results are unchanged
GREEN: Code fix deployed and checked; client acceptance retest remains.
RED: Requirement remains open; implementation/integration is required.
AMBER: Partial fix, manual setup or an unresolved policy decision.
BLUE: Not client-tested / code review only. No client Pass is claimed.
GREY: Existing client Pass retained; no new acceptance claim.
Release f7cd70ae0 (DocuSign). pb_hiring 19.0.2.13.0; pb_hub 19.0.1.12.2. Deployed: payobook, payobook_template, p0clone, rize. 42 recruitment regression tests passed, including 12 DocuSign tests. Deployed Chrome setup/offer controls and role/API checks passed. Six earlier CV-service tests passed. DocuSign demo account creation, credentials, consent and live signing/archive test remain pending; CV hosting is unchanged.